## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 33.5 | 2 |  |  |  | 14 | 2 | 2 | 3 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2016-10-31 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Mon | Wed | Fri | Mon | Wed | Fri | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2016-10-17 | 2016-10-19 | 2016-10-21 | 2016-10-24 | 2016-10-26 | 2016-10-28 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
5 | 1 | Create First Level layout | WS |  | 1 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Assigned
6 | 1 | Create Player, Player Movement Mechanic | WS |  | 4 | 0 | 4 |  | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Active
7 | 2 | End Level, Load Next level function | WS |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Verify?
8 | 1 | Create 'Vacuum' enemy behavior | WS |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
9 | 2 | Create clicking 'leap' function to alter player movment | WS |  | 2 | 0 | 2 |  | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Deferred
10 | 1 | Create 'bad mouse' enemy behavior | WS |  | 4 | 0 | 4 |  | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fact of Life
11 | 2 | Create Subsequent Levels, adding new enemy/mechanic | WS |  | 8 | 0 | 8 |  | 8 | 8 | 8 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Can't Repro
12 | 3 | Add Sprites/animations to Player / enemies | WS |  | 4 | 2 | 2 |  | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
13 | 3 | Add Sounds | WS |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Proper Camera Behavior | WS |  | 2 | 0 | 2 |  | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15
16 | 2 | Add Dog Final Boss | WS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 4 | Add Tail Aesthetic | WS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 3 | Add Dying Animation | WS |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 1 | Title Screen | WS |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 1 | Alter movement to work with yarn rather than mouse | WS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 |  | Make all game scenes connected - transitions | WS |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 |  | Add 'Cheat Codes' | WS |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 |  | Need to prevent Catnip from being placed anywhere, can currently jump out of map | WS |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
108 |  | leaping' a little buggy - bounces extra times | WS |  | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | Reported
109 |  | Strange lock on behavior when multiple bad mice | WS |  | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
110 |  | Weird bug causing tail to go haywire on some collisions | WS |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 14 | 14 | 12 | 10 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 |  | Optimum | [5 empty] | Line | 33.5 | 33.5 | 28.7143 | 23.9286 | 16.75 | 11.9643 | 7.1786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212
213 |  | Sum | [6 empty] | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 13.5 | 13.5 | 10.5 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 |  |  | 2 | [5 empty] | 12.5 | 12.5 | 11.5 | 8.5 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 |  |  | 3 | [5 empty] | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 3.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
218 |  |  | 4 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Will Shellabarger | WS |  |  |  |  | WS | 42.5 | 42.5 | 37.5 | 27.5 | 22.5 | 14.5 | 3 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
223 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 |  | All | ALL |  |  |  |  | ALL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5
236

## Daily Scrum
Producer | 2016-10-31 |  | Team Members
Approved | Dates |  | Will Shellabarger | All
| 2016-10-17 | Mon | Done: Brainstormed new ideas for game, want to do something with a grapple mechanic? Next: hammer out idea more throroughly
| 2016-10-18 | Tue | Done: Nothing today Next: Coninue to Think of game ideas
| 2016-10-19 | Wed | Done: Came up with new game idea - follow mouse mechanic with puzzles Next: Implement first level, basic player movement, camera movement
| 2016-10-20 | Thu | Done: implemented player movment and camera movement. Starting to implement 'leap' mechanic with catnip Next:Polish player movement, create basic 'vacuum' enemy class, finish leap mechanic
| 2016-10-21 | Fri | Done: Finsihed catnip game mechanic to jump over obstacles, created vacuum enemy Next: Create 'badmouse' enemy that distracts the cat
| 2016-10-22 | Sat | Done: Nothing today Next: continue badmouse enemy, create levels to intruduce the new mechanics one by one
| 2016-10-23 | Sun | Done: Finsihed bad mouse, a little buggy still; created levels 1-3 to introduce catnip and bad-mouse game mechanics Next: Create more levels, make game look better (sprites, better shapes, etc.)
| 2016-10-24 | Mon | Done: Gold Spike submission
| 2016-10-25 | Tue | Done: Starting to alter mouse-follow mechanic to follow yarn rather than mouse Next: finish yarn dropping mechanic
| 2016-10-26 | Wed | Done: Finished yarn dropping mechanic, added more textures, colors Next: Work on subsequent level design, final boss
| 2016-10-27 | Thu | Done: Nothing today Next: level design, boss
| 2016-10-28 | Fri | Done: Finished yarn dropping mechanic Next: Work on subsequent level design, final boss
| 2016-10-29 | Sat | Done: Added Tail aesthetic, Added final boss, fixed catnip dropping boundaries Next: Fix badmouse behavior when multiple on screen, add more levels, add sounds
| 2016-10-30 | Sun | Done: Fixed Bad mouse, added 4th level, added death screeens, added sounds Next: Last minute bug fixes
| 2016-10-31 | Mon | Done: Justification Document, prepare for submission
| 2016-11-01 | Tue
| 2016-11-02 | Wed
| 2016-11-03 | Thu
| 2016-11-04 | Fri
| 2016-11-05 | Sat
| 2016-11-06 | Sun
| 2016-11-07 | Mon